## Slide 1
DESIGN REVIEW · GATE 2 OF 6
Phase 2 Exit Gate Review
Requirements Phase (Design Inputs) · CSI-100 Cell Sorting Instrument (IVD)
Item | Detail
Decision requested | Exit Requirements phase; start Development
Review date | 22 January 2026
Document | PGR-CSI-G2 Rev A
Presenter | Atif Lodhi, Systems Engineering
Chair | VP Research and Development
Illustrative example. Product name, people, document numbers and figures are fictional.
Notes: Phase 2 is the Requirements phase. Its exit gate decides whether the design inputs are complete and stable enough to start detailed design.

## Slide 2
GATE QUESTION
Are the design inputs ready for detailed design?
Phase 0
Concept
Exited Dec 2024
Phase 1
Feasibility
Exited May 2025
Phase 2
Requirements
Exit gate today
Phase 3
Development
Exit Aug 2026
Phase 4
Verification
Exit Feb 2027
Phase 5
Validation
Exit May 2027
Phase 6
Transfer
Exit Jun 2027
Go means
The requirements baseline is frozen under change control and detailed design starts.
No-go means
A criterion is not met or an open item blocks design; the phase continues.
How to read this deck
Each evidence slide names the exit criteria it covers and their status, top right.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
2 / 12
Notes: Seven phases per the product development procedure PDP-001; no phase starts before the previous exit gate is approved. Package issued 8 Jan 2026; 187 comments dispositioned; 9 of 9 voting members and an independent reviewer present.

## Slide 3
EXIT CRITERIA SCORECARD · 14 CRITERIA FROM PDP-001
9 met · 5 met with action · 0 not met
1
User needs baselined
Met
Slide 4
2
Requirements approved, stable
Met
Slides 4, 10
3
Source, allocation, method on each
Met
Slide 6
4
Quality review closed
Action A2
Slide 5
5
Needs traced to requirements
Met
Slide 6
6
Software flow-down
Action A1
Slide 6
7
Architecture, interfaces
Action A5
Slide 7
8
Software safety class
Action A3
Slide 7
9
Hazards and risk controls
Action A4
Slide 8
10
Regulatory pathway
Met
RS-CSI-001
11
Verification strategy
Met
VVS-CSI-001
12
Program risks owned
Met
Slide 9
13
Gate 1 actions closed
Met
5 of 5
14
Resources, schedule
Met
PMP-CSI-001
Met
Met with action: satisfied for detailed design; remaining work owned and due before Gate 3
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
3 / 12
Notes: "Met with action" is never used for an item detailed design depends on. Regulatory: 510(k), Class II; EU IVDR Class A under Rule 5, with assays classified separately. Gate 1 actions: beam alignment stability, 561/445 nm laser source, IVD positioning, predicate and pathway, option scope.

## Slide 4
CRITERIA 1, 2 · DESIGN INPUT BASELINE
16 user needs refined into 142 requirements
Met
System requirements derived from each user need (SRS-CSI-001 Rev C)
UN-07 Installation
17
UN-01 Accurate counts
14
UN-09 Guided use
12
UN-08 Daily QC
10
UN-10 Records
10
UN-13 US, EU IVD
9
UN-12 Service
8
UN-02 Sort purity
7
UN-05 Plates, slides
7
UN-04 Throughput
6
UN-03 Multicolor
5
UN-06 Safe use
5
UN-15 Cell sizes
5
UN-16 Optics options
5
UN-11 Temperature
3
UN-14 Carryover
3
Where the 142 come from
User needs
110
Hazards
33
Standards
13
How each will be verified
Test
70
Inspection
33
Demonstration
30
Analysis
11
A requirement can have more than one source or method. User needs unchanged since Gate 1.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
4 / 12
Notes: Every user need has at least three system requirements. 32 requirements come only from hazards or standards, for example electrical safety and labeling. Needs come from PRD-CSI-001, 24 interviews at 11 laboratories and predicate complaint data.

## Slide 5
CRITERION 4 · REQUIREMENT QUALITY
All 61 findings closed; 3 values still to confirm
Met with action · A2
Findings by type (two reviewers per section, INCOSE writing rules)
Vague term
18
Two requirements in one
14
Missing tolerance or units
12
No pass/fail criterion
9
States a solution
8
Every finding was corrected in SRS Rev C and re-checked.
Still to be confirmed (TBR) or defined (TBD)
TBR-01 · SYS-471 carryover limit: 1.0% held, 0.5% target
TBR-02 · SYS-543 clog response: 5 s held, 2 s target
TBD-03 · Section 12 transport and installation
Open TBD and TBR items by SRS revision
41
Rev A
Nov 2024
23
Rev B
May 2025
3
Rev C
Jan 2026
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
5 / 12
Notes: The three remaining items need data from Development: the carryover study, clog response measured on DV prototypes, and the shipping study. They close in SRS Rev D, the verification baseline in August 2026. None blocks detailed design.

## Slide 6
CRITERIA 3, 5, 6 · TRACEABILITY
Eight of nine trace links are complete
Met with action · A1
User need → system requirement
16 / 16
System requirement → source
142 / 142
System requirement → allocation
142 / 142
System requirement → verification method
142 / 142
Hazard → control requirement
14 / 14
Software requirement ← SS-10 requirement
29 / 38
Software requirement → parent
131 / 131
Software requirement → software item
131 / 131
User need → planned validation study
16 / 16
The gap is SYS-701 to 709 (Part 11 and cybersecurity), added in SRS Rev C this month. Links to design outputs and test protocols are Gate 3 criteria.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
6 / 12
Notes: Links are held in the requirements tool and the matrix TM-CSI-DT-01 is exported from it, not maintained by hand. SYS-701 to 709 cover user roles, audit trail, electronic signature, locked assays, export, communication loss, locked OS image, SBOM process and data protection; they flow into SRS-SW-CSI-010 Rev D in February (A1).

## Slide 7
CRITERIA 7, 8 · ARCHITECTURE AND SOFTWARE
Every requirement has a home in the architecture
Met with action · A3, A5
System requirements allocated to each subsystem
System level (no one owner)
39
SS-10 Software
38
SS-01 Fluidics
19
SS-06 Electronics
17
SS-07 Sort mechanism
16
SS-04 Excitation optics
14
SS-05 Detection
9
SS-02 Sample delivery
8
SS-08 Sort collection
7
SS-03 Flow cell, nozzle
5
SS-09 Aerosol
3
Shared requirements count once per subsystem. Interfaces: 7 of 8 ICDs released; fluidics umbilical ICD-CSI-003 in draft (A5).
Software baseline
131 software requirements, 12 software items, 14 SOUP components.
IEC 62304 Class B
Laser, pressure and motion hazards are stopped by hardware; wrong results by QC and assay controls.
Condition (A3)
Only the controller firmware removes high voltage today. An independent hardware safety supervisor is added in SAD Rev B.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
7 / 12
Notes: Software carries the most requirements of any subsystem, which is why its flow-down (A1) and safety class (A3) are watched closely. The independent reviewer challenged Class B: without an independent HV path, the controller firmware would be Class C. The board accepted Class B conditional on A3.

## Slide 8
CRITERION 9 · PRODUCT HAZARDS (HA-CSI-001 REV B)
Every hazard is controlled by requirements
Met with action · A4
Hazard
Initial risk
Control requirements
HA-04 Infectious aerosol
Unacceptable
5
HA-01 Laser radiation
Unacceptable
4
HA-02 High voltage
Unacceptable
4
HA-08 Incorrect result
Unacceptable
4
HA-07 Wrong sort output
Unacceptable
2
HA-05 Sort chamber access
Unacceptable
1
HA-15 Fluid run-out
Unacceptable
1
HA-12 Mains, fire
Review
4
HA-09 Stored pressure
Review
2
HA-14 Misconnection
Review
2
HA-13 EMC
Review
1
HA-06 Moving parts
Acceptable
5
HA-10 Chemicals
Acceptable
1
HA-11 Mass, stability
Acceptable
1
14 / 14
hazards with at least one control requirement
33
system requirements are risk controls
Open (A4)
Security threats not yet a hazard source.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
8 / 12
Notes: Initial risk is before any control. Residual risk is estimated but not credited until the controls are verified. HA-03 was merged into HA-04 in Rev B. A requirement can control more than one hazard (for example SYS-1103 labels), so the bars add to more than 33.

## Slide 9
CRITERION 12 · PROGRAM RISKS (RR-CSI-001)
Six risks, each with an owner
Met
Low
Medium
High
High
PR-03
Medium
PR-04
PR-06
PR-01
PR-02
Low
PR-05
Rows: likelihood · Columns: impact
ID | Risk and mitigation | Owner | Rating
PR-01 | Single laser supplier; second source and change notice clause (A6) | Supply Chain | M / H
PR-02 | Purity at 70 µm, 4-way sort; margin study Apr 2026 | R&D | M / H
PR-03 | Options add 6 weeks; separate work package | Program | H / M
PR-04 | Late Part 11 and security scope; A1, SAD Rev B | Software | M / M
PR-05 | Thermal margin, 6 lasers at 30 °C; confirm on DV | R&D | L / H
PR-06 | IVDR notified body capacity for assays | Regulatory | M / M
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
9 / 12
Notes: Rating is likelihood / impact. PR-01 is the top risk: the supplier is a single source for two wavelengths, and nothing today obliges it to tell us about firmware or process changes. Program risks are reviewed monthly; product safety risks are in the risk management file.

## Slide 10
CRITERION 2 · REQUIREMENT STABILITY
Changes are below threshold for two months
Met
Approved requirement change requests per month, Jun 2025 to Jan 2026
9
Jun
14
Jul
11
Aug
7
Sep
12
Oct
6
Nov
4
Dec
2
Jan
Threshold: 5 per month
Rev B (117) to Rev C (142)
Added
31
Modified
44
Deleted
6
The October peak is the option scope decision (aerosol, plates, temperature). Outlined bars are under threshold.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
10 / 12
Notes: 65 change requests from June 2025 to January 2026. PDP-001 uses two consecutive months under 5 as the stability indicator for this gate. After the gate, changes go through formal design change control.

## Slide 11
CARRIED ACTIONS · PATH TO GATE 3
Seven actions, all due before Gate 3
0 blocking
Action · owner
Feb
Mar
Apr
May
Jun
Jul
Aug
G3
A1 Software flow-down of SYS-701 to 709 · P. Nair
27 Feb
A5 Release umbilical ICD-CSI-003 · J. Whitfield
20 Mar
A3 Independent HV safety supervisor · P. Nair
31 Mar
A4 Security threats in hazard analysis · M. Serrano
30 Apr
A6 Laser second source, change notice · Supply
30 Jun
A7 Draft V&V plan VVP-CSI-001 · V&V lead
31 Jul
A2 Close TBR-01, TBR-02, TBD-03 · A. Lodhi
14 Aug
Blocking items: two found in pre-review (an interlock requirement with no verification method; conflicting HV limits), both fixed in SRS Rev C.
Gate 3 requires: no TBD or TBR, every requirement traced to a design output and a test protocol, and A1 to A7 closed.
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
11 / 12
Notes: Bars run from today (22 Jan) to each due date; the dashed line is the Gate 3 review in late August. A1 is due first because the software design review depends on it. Actions are tracked in AIL-CSI-G2 and reported at each monthly program review.

## Slide 12
PHASE 2 EXIT GATE · RECOMMENDATION
Go: exit Phase 2, start Development
No criterion is unmet and nothing blocks detailed design.
Freeze the baseline
SRS Rev C and HA-CSI-001 Rev B go under design change control
Track the conditions
A1 to A7 reported at each monthly program review
Next gate
Phase 3 exit, the verification baseline, August 2026
CSI-100 · Phase 2 Exit Gate Review · PGR-CSI-G2 Rev A
12 / 12
Notes: A no-go would be warranted if any criterion were not met or an open item blocked detailed design. Neither applies.